## Sheet1
Automoto Creation Timeline
Task | Start | End | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Programming | 1 | 15
Sensor Reading | 1 | 1 | bar: 1
Stepper Control | 2 | 2 | bar: 2
Motor Sensor Feedback | 2 | 4 | bar: 2 to 4
Drive Motor Control | 2 | 2 | bar: 2
Wireless Integration | 3 | 4 | bar: 3 to 4
PID Control | 2 | 15
Xbee Interfacing | 10 | 13 | bar: 10 to 13
Actuator Control | 9 | 10 | bar: 9 to 10
Wheels | 2 | 9 | bar: 2 to 9
Manufacturing
Dimension Verification | 2 | 2 | bar: 2
BOM/Wheel Selection | 2 | 2 | bar: 2
Fabrication
Testing Wheels | 2 | 3 | bar: 2 to 3
Actuator
Pnumatic Actuator Selection | 5 | 7 | bar: 5 to 7
Fabrication of A-Arms | 7 | 9 | bar: 7 to 9